## Sheet1
ID | User Story | Sprint Number | Story Priority | Story Type | Story Status | Story Points
1 | Create user stories | 0 | H | Documentation | Done | 3
2 | As a user, I want to be able to upload a PDF of my syllabus for parsing so that the schedule may be extracted. | not assigned | H | Code | Waiting | 8
3 | As a user, I want to be able to export my calendar as a downloadable .ics file so I can put my assignments into my calendar. | 3 | H | Code | In-Progress | 8
5 | As a user, I want to be able to automatically extract due dates from my syllabus into my calendar, as this saves me time. | not assigned | H | Code | Waiting | 6
6 | As a user, I want to be able to automatically extract exam dates from my syllabus into my calendar, as this saves me time. | not assigned | H | Code | Waiting | 7
7 | As a user, I want the ability to manually input assignments and their dates that the parser might miss or that the syllabus doesn’t include, so that I can make a comprehensive schedule. | 3 | H | Code | In-Progress | 4
8 | As a user, I want to be able to view and edit the information collected from the syllabus to ensure its accuracy. | not assigned | H | Code | Waiting | 3
9 | As a user, I want to be able to undo and redo recent edits so that mistakes can be avoided. | not assigned | M | Code | Waiting | 2
10 | As a user, I want to be able to add descriptions to events so that I can better understand the assignment at a glance. | not assigned | M | Code | Waiting | 1
11 | As a user, I want to be able to select which assignments or events are included in the calendar, so that it does not become cluttered with unnecessary information. | not assigned | H | Code | Waiting | 1
12 | As a user, I want the parser to indicate sections that it was unable to interpret so that I may choose to manually enter the information if I believe it is important. | not assigned | H | Code | Waiting | 6
13 | As a user, I want the most heavily weighted assignments to be highlighted by the parser so that I can best understand what to include in my calendar. | not assigned | L | Code | Waiting | 8
14 | As a user, I want to be able to categorize events by more than just their names using tags for better customization. | not assigned | M | Code | Waiting | 4
15 | As a user, I want to be able to choose the time/date system used by the parser so that I can be sure it works for me. | not assigned | H | Code | Waiting | 3
16 | As a user, I want the parser to understand different date formats so that it works with more syllabi. | not assigned | H | Code | Waiting | 3
17 | As a user, I want to upload multiple syllabi at once, so that the syllabi parser can filter through all of my syllabi at once instead of one at a time. | not assigned | H | Code | Waiting | 2
18 | As a user, I want to be able to extract a professor's office hours as an optional event so that I remember when help is available. | not assigned | M | Code | Waiting | 2
19 | Create problem statements | 0 | H | Documentation | Done | 3
20 | Create product backlog | 1 | H | Documentation | Done | 2
21 | Create sprint backlog | 1 | H | Documentation | Done | 2
22 | Update sprint backlog after review | 1 | M | Documentation | Done | 1
23 | Create software requirements specification | 1 | H | Documentation | Done | 3
24 | Create sprint review for sprint 1 | 1 | M | Documentation | Done | 1
25 | Create Kanban Board | 1 | H | Documentation | Done | 1
26 | Create Quality Checking Policy | 1 | M | Documentation | Done | 1
27 | Set Up Build Environment | 1 | M | Code | Done | 2
28 | Edit README with build instructions | 1 | L | Documentation | Done | 1
29 | Compile screenshots of the App running on everyone's computers | 1 | M | Code | Done | 1
30 | Create UI Mockups | 1 | H | Documentation | Done | 2
31 | Create Architecture Design Document | 2 | H | Documentation | Done | 2
32 | Update Kanban | 2 | M | Documentation | Done | 1
33 | Create Prototype for Usability Testing | 2 | H | Documentation | Done | 2
34 | Create Use Case Descriptions and Diagrams | 2 | H | Documentation | Done | 2
35 | Create sprint review for sprint 2 | 2 | M | Documentation | Done | 1
36 | Create sprint backlog for sprint 2 | 2 | H | Documentation | Done | 1
37 | Create Basic React Wireframe | 2 | H | Code | Done | 2
38 | Create Sprint Review for sprint 3 | 3 | M | Documentation | In-Progress | 1
39 | Create sprint backlog for sprint 3 | 3 | H | Documentation | In-Progress | 2
40 | Create Progress Video for sprint 3 | 3 | H | Documentation | In-Progress | 4
41 | Create Domain Model | 3 | H | Documentation | In-Progress | 5
42 | Set up Continuous Intergration | 3 | H | Code | In-Progress | 3
43 | Update Kanban | 3 | M | Documentation | In-Progress | 1
44 | Create Roadmap for sprint 3 | 3 | L | Documentation | In-Progress | 1