## Sheet1
ID | User Story | Sprint Number | Story Priority | Story Type | Story Status | Story Points
Revisions are named "[Original_ID]R[Sprint#_Revised]
Sprint 1
20 | Create product backlog | 1 | H | Documentation | Done | 2
21 | Create sprint backlog | 1 | H | Documentation | Done | 2
22 | Update sprint backlog after review | 1 | M | Documentation | Done | 1
23 | Create software requirements specification | 1 | H | Documentation | Done | 3
24 | Create sprint review for sprint 1 | 1 | M | Documentation | Done | 1
25 | Create Kanban Board | 1 | H | Documentation | Done | 1
26 | Create Quality Checking Policy | 1 | M | Documentation | Done | 1
27 | Set Up Build Environment | 1 | M | Code | Done | 2
28 | Edit README with build instructions | 1 | L | Documentation | Done | 1
29 | Compile screenshots of the App running on everyone's computers | 1 | M | Code | Done | 1
30 | Create UI Mockups | 1 | H | Documentation | Done | 2
1R1 | Revise user stories | 1 | H | Revision | Done | 1
19R1 | Revise problem statements | 1 | H | Revision | Done | 1
Sprint 2
31 | Create Architecture Design Document | 2 | H | Documentation | Done | 2
32 | Update Kanban | 2 | M | Documentation | Done | 1
33 | Create Prototype for Usability Testing | 2 | H | Documentation | Done | 2
34 | Create Use Case Descriptions and Diagrams | 2 | H | Documentation | Done | 2
35 | Create sprint review for sprint 2 | 2 | M | Documentation | Done | 1
36 | Create sprint backlog for sprint 2 | 2 | H | Documentation | Done | 1
37 | Create Basic React Wireframe | 2 | H | Code | Done | 2
23R2 | Revise SRS | 3 | H | Revision | Done | 2
20R2 | Revise Product Backlog | 3 | M | Revision | Done | 1
21R2 | Revise Sprint Backlog | 3 | M | Revision | Done | 1
Sprint 3
38 | Create Sprint Review for sprint 3 | 3 | M | Documentation | In-Progress | 1
39 | Create sprint backlog for sprint 3 | 3 | H | Documentation | In-Progress | 2
40 | Create Progress Video for sprint 3 | 3 | H | Documentation | In-Progress | 4
41 | Create Domain Model | 3 | H | Documentation | In-Progress | 5
42 | Set up Continuous Intergration | 3 | H | Code | In-Progress | 3
43 | Update Kanban | 3 | M | Documentation | In-Progress | 1
44 | Create Roadmap for sprint 3 | 3 | L | Documentation | In-Progress | 1
3 | As a user, I want to be able to export my calendar as a downloadable .ics file so I can put my assignments into my calendar. | 3 | H | Code | In-Progress | 8
7 | As a user, I want the ability to manually input assignments and their dates that the parser might miss or that the syllabus doesn’t include, so that I can make a comprehensive schedule. | 3 | H | Code | In-Progress | 4
23R3 | Revise SRS | 3 | M | Revision | In-Progress | 2
20R3 | Revise Product Backlog | 3 | M | Revision | In-Progress | 1
21R3 | Revise sprint backlog | 3 | M | Revision | In-Progress | 1
31R3 | Revise Architecture Design | 3 | H | Revision | In-Progress | 1
34R3 | Revise Use Case Diagrams | 3 | M | Revision | In-Progress | 2
26R3 | Revise Quality Checking Policy | 3 | H | Revision | In-Progress | 1
28R3 | Revise README | 3 | M | Revision | In-Progress | 1